# Hyderabad Intelligence  Platform

# Implementation Timeline & Execution Plan

Document Type: Project Scaling Timeline

Date: February 15, 2026

Version: 1.0

Start Date: February 19, 2026 (Thursday)

Target Completion: March 28, 2026

______________________________________________________________________________

# 1. Executive Summary

This document outlines the execution plan for scaling the Real Estate Intelligence Platform from a 7-location Proof of Concept (West Hyderabad) to a production-grade system covering ~300 micro-market locations across all of Hyderabad.

The current system has a fully validated pipeline — web scraping, FinBERT sentiment analysis, PostGIS aggregation, and interactive map visualization — operational for 7 locations. The objective is to extend this pipeline city-wide while maintaining data quality, system reliability, and platform performance.

## Current Baseline

| Metric | Status |
| --- | --- |
| Locations with full pipeline (Scrape → FinBERT → Scores) | 7 (West Hyderabad) |
| Locations with CSV-imported data only | ~293 |
| Total target locations | ~300 |
| Working infrastructure | PostgreSQL + PostGIS, FastAPI, MapLibre GL, Playwright Scrapers |
| Sentiment model | FinBERT (ProsusAI/finbert) — validated |
| Frontend | Interactive vector map with Intel Card, search, layers |

## Scaling Objective

| From | To |
| --- | --- |
| 7 locations with real sentiment | ~300 locations with real sentiment |
| Manual scraping triggers | Automated bi-weekly refresh cycle |
| Single-area coverage | City-wide coverage (all Hyderabad zones) |
| Development environment | Production-ready deployment |

______________________________________________________________________________

# 2. Phase Breakdown

## Phase 1: Scraping Architecture Overhaul

Duration: 5 days (Feb 19 – Feb 25)

Objective: Transform the scraping system from individual-location queries to a city-wide harvesting model capable of covering ~300 locations efficiently.

### Why the Current Approach Won't Scale

The existing scraper (scrape_playwright.py) fires queries like "Gachibowli Hyderabad real estate" — one query per location. For 300 locations across 5 themes, that's 1,500 queries, which will:

Trigger Google's anti-bot defenses

Take days to complete

Miss cross-location articles

### The Solution: Inverted Scraping + NER Tagging

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 1 (Thu, Feb 19) | Design the Inverted Scraping architecture | Architecture document + flow diagram |
| — Define city-wide query templates (e.g., "Hyderabad real estate 2026", "Hyderabad metro infrastructure") |  |  |
| — Map out 8-10 broad query categories covering: Real Estate, Infrastructure, Transport, Lifestyle, Safety, Corporate, Education, Healthcare |  |  |
| Day 2 (Fri, Feb 20) | Build the Named Entity Recognition (NER) Tagger | Working NER module |
| — Create a location registry of all ~300 location names + aliases (e.g., "Gachi" → "Gachibowli", "HITEC City" → "Hi-Tech City") |  |  |
| — Implement fuzzy matching logic for location detection in article text |  |  |
| — Test NER accuracy on sample articles (target: >90% precision) |  |  |
| Day 3 (Sat, Feb 22) | Re-architect the Playwright scraper for city-wide queries | Modified scrape_playwright.py |
| — Implement proxy rotation system (to avoid IP blocking) |  |  |
| — Add rate limiting (2-3 second delays between requests) |  |  |
| — Build retry logic with exponential backoff |  |  |
| Day 4 (Mon, Feb 24) | Build a scraping queue & job management system | Queue system + logging |
| — Track which queries have been executed & when |  |  |
| — Implement incremental scanning (only fetch articles newer than last run) |  |  |
| — Add deduplication logic (same article appearing in multiple queries) |  |  |
| Day 5 (Tue, Feb 25) | Execute the first full city-wide scrape (2024-2026 data) | Raw articles in database |
| — Run all query templates across Google News RSS |  |  |
| — Tag articles to locations via NER |  |  |
| — Store in raw_articles table with metadata (source, date, location_id, raw_text) |  |  |
| — Expected yield: 3,000–6,000 articles |  |  |

### Phase 1 Exit Criteria

☐ City-wide scraper operational and tested

☐ NER tagger achieving >90% location-matching accuracy

☐ 3,000+ raw articles harvested and stored in database

☐ Articles tagged to their respective locations

☐ Proxy rotation and rate limiting active

______________________________________________________________________________

## Phase 2: FinBERT Sentiment Processing at Scale

Duration: 4 days (Feb 26 – Mar 1)

Objective: Process all harvested articles through FinBERT and generate real sentiment scores for ~300 locations.

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 6 (Wed, Feb 26) | Set up GPU processing environment | GPU pipeline ready |
| — Configure Google Colab Pro (or local GPU if available) |  |  |
| — Create batch processing script (process 200-500 articles per batch) |  |  |
| — Implement progress tracking & checkpointing (resume if interrupted) |  |  |
| Day 7 (Thu, Feb 27) | Run FinBERT inference — Batch 1 | ~50% articles processed |
| — Process first half of articles (~1,500–3,000) |  |  |
| — Store per-article sentiment scores in processed_sentiment_data table |  |  |
| — Monitor for quality: spot-check 20 articles manually |  |  |
| Day 8 (Fri, Feb 28) | Run FinBERT inference — Batch 2 | All articles processed |
| — Process remaining articles |  |  |
| — Validate: ensure every article has a sentiment score |  |  |
| — Generate processing report (articles per location distribution) |  |  |
| Day 9 (Sat, Mar 1) | Score Aggregation & Database Update | Updated location_insights |
| — Run aggregation logic: calculate weighted average sentiment per location |  |  |
| — Compute derived scores: growth_score, investment_score from sentiment + infrastructure data |  |  |
| — Update location_insights table: replace CSV-based scores with real FinBERT-derived scores |  |  |
| — Validation: Compare old (CSV) vs new (FinBERT) scores for 20 sample locations |  |  |

### Phase 2 Exit Criteria

☐ All harvested articles processed through FinBERT

☐ Sentiment scores stored in processed_sentiment_data

☐ Aggregated scores computed for all ~300 locations

☐ location_insights table updated with real sentiment-derived scores

☐ Quality validation passed on sample locations

______________________________________________________________________________

## Phase 3: Price Trends & Analytics Enhancement

Duration: 3 days (Mar 3 – Mar 5)

Objective: Ensure price trend data and analytics features are complete and accurate for all ~300 locations.

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 10 (Mon, Mar 3) | Price data validation & gap-filling | Complete price_trends table |
| — Audit existing price data for all 300 locations |  |  |
| — Identify locations with missing or incomplete price history |  |  |
| — Backfill missing data using interpolation + scraped price signals |  |  |
| — Validate price trends against known market benchmarks |  |  |
| Day 11 (Tue, Mar 4) | Build enhanced analytics APIs | New API endpoints |
| — Location comparison endpoint (compare 2-5 locations side-by-side) |  |  |
| — "Trending" detection (identify locations with sharp score changes) |  |  |
| — City-wide statistics endpoint (avg price, top performers, declining areas) |  |  |
| Day 12 (Wed, Mar 5) | Frontend integration for new analytics | Updated UI |
| — Wire new API endpoints to Price Trends page |  |  |
| — Add comparison charts (Chart.js multi-location overlay) |  |  |
| — Display city-wide market summary stats |  |  |

### Phase 3 Exit Criteria

☐ Price trends available for all ~300 locations

☐ Comparison and trending APIs functional

☐ Price Trends page displays real, accurate data

☐ City-wide statistics rendering correctly

______________________________________________________________________________

## Phase 4: Frontend Polish & Production Readiness

Duration: 4 days (Mar 6 – Mar 11)

Objective: Ensure the platform is polished, performant, and ready for corporate-level demonstration.

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 13 (Thu, Mar 6) | Map performance optimization for 300 pins | Optimized map rendering |
| — Implement marker clustering for dense areas |  |  |
| — Optimize GeoJSON payload size (compression, field trimming) |  |  |
| — Add lazy loading for Intel Card data (fetch on click, not on load) |  |  |
| Day 14 (Fri, Mar 7) | Intel Card refinement with real data | Enhanced Intel Card |
| — Ensure all 300 locations show real FinBERT-based smart copy |  |  |
| — Verify dynamic facts are data-driven (not placeholder text) |  |  |
| — Test edge cases: locations with very few articles, extreme scores |  |  |
| Day 15 (Mon, Mar 10) | Mobile responsiveness & cross-browser testing | Responsive UI |
| — Test and fix layout on mobile (phones, tablets) |  |  |
| — Verify map interactions work on touch devices |  |  |
| — Cross-browser testing: Chrome, Firefox, Edge, Safari |  |  |
| Day 16 (Tue, Mar 11) | UI/UX final polish | Production-quality interface |
| — Smooth all animations and transitions |  |  |
| — Add loading states, error handling, empty states |  |  |
| — Final visual QA pass |  |  |

### Phase 4 Exit Criteria

☐ Map renders 300 pins smoothly (<3 second load time)

☐ All Intel Cards display real, FinBERT-derived insights

☐ Responsive design verified on mobile/tablet

☐ No visual bugs or broken interactions

______________________________________________________________________________

## Phase 5: Automation & Continuous Intelligence Loop

Duration: 3 days (Mar 12 – Mar 14)

Objective: Set up the automated refresh cycle so the platform stays current without manual intervention.

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 17 (Wed, Mar 12) | Build incremental scraping script | Auto-refresh scraper |
| — Modify scraper to only fetch articles from the last 2 weeks |  |  |
| — Implement "last_scraped" timestamp tracking per query category |  |  |
| — Add NER tagging to incremental pipeline |  |  |
| Day 18 (Thu, Mar 13) | Implement automated scheduling & moving average updates | Scheduled automation |
| — Set up Windows Task Scheduler (or cloud-based cron) |  |  |
| — Schedule: Run every 2 weeks (Sunday 2:00 AM) |  |  |
| — Implement moving average score update: fold new data into existing scores |  |  |
| — Build error notification system (email/log alert if scraper fails) |  |  |
| Day 19 (Fri, Mar 14) | End-to-end automation test | Validated automation pipeline |
| — Trigger a manual run of the full loop: Scrape → FinBERT → Aggregate → Update DB |  |  |
| — Verify scores update correctly in the database |  |  |
| — Verify frontend reflects the new scores |  |  |
| — Document the automation setup (runbook) |  |  |

### Phase 5 Exit Criteria

☐ Incremental scraper fetches only recent articles

☐ Automation schedule configured and tested

☐ Moving average update logic validated

☐ Full loop executes without manual intervention

☐ Runbook documentation complete

______________________________________________________________________________

## Phase 6: Deployment & Launch

Duration: 4 days (Mar 17 – Mar 20)

Objective: Deploy the platform to production infrastructure accessible for corporate use.

| Day | Task | Deliverable |
| --- | --- | --- |
| Day 20 (Mon, Mar 17) | Backend deployment | Live backend API |
| — Deploy FastAPI + Uvicorn to cloud server (Render / AWS / DigitalOcean) |  |  |
| — Migrate PostgreSQL + PostGIS to managed cloud database |  |  |
| — Configure environment variables, connection pooling, CORS |  |  |
| Day 21 (Tue, Mar 18) | Frontend deployment | Live frontend |
| — Deploy frontend to static hosting (Vercel / GitHub Pages / Netlify) |  |  |
| — Configure custom domain (if applicable) |  |  |
| — Set up SSL/HTTPS |  |  |
| Day 22 (Wed, Mar 19) | Security & hardening | Hardened production environment |
| — Configure firewall rules (restrict DB access) |  |  |
| — Set up API rate limiting (prevent abuse) |  |  |
| — Database backup strategy (daily automated backups) |  |  |
| — Health check endpoint + uptime monitoring |  |  |
| Day 23 (Thu, Mar 20) | Final testing & documentation | Production-ready system |
| — End-to-end smoke test on production |  |  |
| — API documentation (Swagger/OpenAPI) |  |  |
| — User guide / demo walkthrough |  |  |
| — 🚀 LAUNCH |  |  |

### Phase 6 Exit Criteria

☐ Backend API live and responding (<500ms latency)

☐ Frontend accessible via public URL

☐ SSL/HTTPS configured

☐ Database backups operational

☐ Documentation complete

______________________________________________________________________________

# 3. Master Timeline (Gantt View)

Week 1 (Feb 19-25)  ████████████████████  Phase 1: Scraping Architecture
Week 2 (Feb 26-Mar 1) ██████████████████  Phase 2: FinBERT at Scale
Week 3 (Mar 3-5)     ████████████         Phase 3: Price Trends & Analytics
Week 3-4 (Mar 6-11)  ████████████████     Phase 4: Frontend Polish
Week 4 (Mar 12-14)   ████████████         Phase 5: Automation
Week 5 (Mar 17-20)   ████████████████     Phase 6: Deployment & Launch

| Week | Dates | Phase | Key Milestone |
| --- | --- | --- | --- |
| Week 1 | Feb 19 – Feb 25 | Scraping Architecture | 3,000+ articles harvested, NER tagger operational |
| Week 2 | Feb 26 – Mar 1 | FinBERT Processing | All ~300 locations have real sentiment scores |
| Week 3 | Mar 3 – Mar 5 | Price Trends | Complete price analytics for all locations |
| Week 3-4 | Mar 6 – Mar 11 | Frontend Polish | Production-quality, mobile-ready interface |
| Week 4 | Mar 12 – Mar 14 | Automation | Self-updating bi-weekly intelligence loop |
| Week 5 | Mar 17 – Mar 20 | Deployment | 🚀 Production Launch |

______________________________________________________________________________

# 4. Risk Register

| # | Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | Google blocks scraper IPs during city-wide harvest | High | Critical | Proxy rotation, rate limiting (2-3s delays), residential proxy fallback |
| R2 | FinBERT processing exceeds GPU time estimates | Medium | High | Use Google Colab Pro ($10/mo), implement checkpointing to resume |
| R3 | NER tagger misidentifies locations (<90% accuracy) | Medium | High | Maintain comprehensive alias dictionary, implement fuzzy matching, manual QA on sample |
| R4 | Insufficient articles for some locations | Medium | Medium | Retain CSV-based scores as fallback for locations with <5 articles; flag for manual review |
| R5 | Database performance degrades at 300 locations | Low | Medium | Add PostgreSQL indexing, implement API response caching |
| R6 | Deployment environment configuration issues | Low | Medium | Use containerization (Docker), document all env variables |

______________________________________________________________________________

# 5. Resource Requirements

## Infrastructure

## Tools & Stack

| Layer | Technology |
| --- | --- |
| Scraping | Playwright (Async), BeautifulSoup, Google News RSS |
| NLP/AI | FinBERT (ProsusAI/finbert), Hugging Face Transformers |
| Database | PostgreSQL 15 + PostGIS |
| Backend | FastAPI, Uvicorn (ASGI) |
| Frontend | MapLibre GL JS, PMTiles, Chart.js, Vanilla JS/CSS |
| Deployment | Render / Vercel / GitHub Pages |

# 6. Success Criteria

## Technical KPIs

| Metric | Target |
| --- | --- |
| Locations with real FinBERT sentiment | ~300 |
| Sentiment accuracy (manual validation) | >85% agreement |
| API response time | <500ms (p95) |
| Map load time | <3 seconds |
| Automated refresh cycle | Bi-weekly (every 14 days) |
| System uptime | >99% |

## Business KPIs

| Metric | Target |
| --- | --- |
| Hyderabad coverage | All major micro-markets |
| Data freshness | Scores updated within 14 days of new data |
| User experience | Mobile-responsive, professional-grade UI |
| Documentation | Complete API docs + user guide |

______________________________________________________________________________

# 7. Delivery Summary

| Item | Date |
| --- | --- |
| Project Start | Thursday, February 19, 2026 |
| Data Pipeline Complete | Saturday, March 1, 2026 |
| Analytics & UI Complete | Tuesday, March 11, 2026 |
| Automation Operational | Friday, March 14, 2026 |
| 🚀 Production Launch | Thursday, March 20, 2026 |
| Total Duration | ~5 weeks (23 working days) |

______________________________________________________________________________

This document is a living plan and will be updated as phases are completed.

Last updated: February 15, 2026